## Project Plan
SEJEL Restaurant — Point of Sale
Project plan · delivered scope and remaining scope
Branch: Olaya · Prepared 12 Aug 2026 · Dates for delivered work are the actual commit dates. Dates for remaining work are ESTIMATES (blue), on a Sunday–Thursday working week.
ID | Phase | Workstream | Scope / deliverable | Status | Owner | Effort (working days) | Start | Finish | Calendar days | % complete | Evidence / notes
1 | Foundations | Architecture & repository | Flutter till, FastAPI backend, ZATCA library, PixelPoint migration — one repo, four parts | Done | Development | 1 | 2026-08-04 | 2026-08-04 | 1 | 100% | commit 6cdfe13
2 | Foundations | ZATCA signing on the device | Dart signer pinned byte-for-byte to the Python reference via golden vectors | Done | Development | 0.16 | 2026-08-05 | 2026-08-05 | 1 | 100% | commit 86c4bc1
3 | Foundations | Printer Setup | Device setup screen: printer address, port, test slip through the real ESC/POS builder | Done | Development | 0.16 | 2026-08-05 | 2026-08-05 | 1 | 100% | commits b2c8370, 69c4df3
4 | Foundations | Windows desktop target | The till runs as a Windows application | Done | Development | 0.16 | 2026-08-05 | 2026-08-05 | 1 | 100% | commit eb84074
5 | Foundations | Till Setup / device enrolment | Enrolment codes, device identity, roles (till / KDS / CDS), remembered sale type | Done | Development | 0.16 | 2026-08-05 | 2026-08-05 | 1 | 100% | commits c86abb0, f10021c
6 | Foundations | Back office foundation | Sign-in, dashboard, price editing, device enrolment | Done | Development | 0.16 | 2026-08-05 | 2026-08-05 | 1 | 100% | commit c86abb0
7 | Foundations | Real catalog migration | 560 products, 42 screens, 11 sale types loaded from the customer's PixelPoint data | Done | Development | 0.16 | 2026-08-05 | 2026-08-05 | 1 | 100% | commit cd551a3
8 | Catalog & menu | Order numbers | Reserved in blocks from the backend so two tills never call the same number | Done | Development | 0.16 | 2026-08-10 | 2026-08-10 | 1 | 100% | commit b3e47b0
9 | Catalog & menu | Tablet schema migrations | An installed till survives an app update instead of failing on a missing column | Done | Development | 0.16 | 2026-08-10 | 2026-08-10 | 1 | 100% | commit 7fccf52
10 | Catalog & menu | Product master | Products, prices across 10 tiers, kitchen routing, report category, till button look | Done | Development | 0.16 | 2026-08-10 | 2026-08-10 | 1 | 100% | commits a5a43ac, 8a94a27
11 | Catalog & menu | Menu layout editor | Pages, the menu grid a till lands on, drag-free placement of buttons | Done | Development | 0.16 | 2026-08-10 | 2026-08-10 | 1 | 100% | commits c2d002c, 7b7fe66, 14340f2
12 | Catalog & menu | Modifiers on the till | Meal-deal prompts asked before an item can be rung; choices reach the bill and the kitchen | Done | Development | 0.16 | 2026-08-10 | 2026-08-10 | 1 | 100% | commits 8b29bbf, a6fc72d
13 | Catalog & menu | Button pictures | Crop-and-upload in the back office, image + name + price on one till tile | Done | Development | 0.14 | 2026-08-11 | 2026-08-11 | 1 | 100% | commit 839e6a0
14 | Payments & service | Payment Mode on the till | One bill across several tenders, cash change, split payment | Done | Development | 0.14 | 2026-08-11 | 2026-08-11 | 1 | 100% | commit e4033df
15 | Payments & service | Dine-in: floor and checks | Floor plan, seating, save the check, send rounds to the kitchen | Done | Development | 0.14 | 2026-08-11 | 2026-08-11 | 1 | 100% | commits d96348a, c65dd61
16 | Payments & service | Tables pushed together | Two twos make a four: one party, one order, one bill | Done | Development | 0.14 | 2026-08-11 | 2026-08-11 | 1 | 100% | commit a3a7af9
17 | Payments & service | Floor areas | A restaurant is not one room: areas, closing an area, tidy grid alignment | Done | Development | 0.14 | 2026-08-11 | 2026-08-11 | 1 | 100% | commits 7180d42, 5e535b0, ecdfaca
18 | Payments & service | Split the check between guests | Each guest's share is its own sale and its own tax invoice; table closes when nothing is owed | Done | Development | 0.14 | 2026-08-11 | 2026-08-11 | 1 | 100% | commit a0bb72b
19 | Payments & service | Table master | Tables are set up, then called onto a plan — the split the menu already had | Done | Development | 0.14 | 2026-08-11 | 2026-08-11 | 1 | 100% | commit 224f1b0
20 | Payments & service | Branding on till and receipt | Seller and branch read from the device, not compiled in | Done | Development | 0.5 | 2026-08-12 | 2026-08-12 | 1 | 100% | commit e700690
21 | Payments & service | Receipt on screen | The same bytes the printer gets, decoded back, with a scannable ZATCA QR | Done | Development | 0.5 | 2026-08-12 | 2026-08-12 | 1 | 100% | commit 69c4df3
22 | Setup modules | Employee Setup | Staff sync to the till and the cashier picker are live. | In progress | Development | 0.16 | 2026-08-13 | 2026-08-13 | 1 | 35% | Staff sync to the till and the cashier picker are live. Pending: staff master in the back office, PIN set and reset, roles. Migrated staff arrive with must_set_pin and no hash.
23 | Setup modules | Security Setup | Back-office sign-in, roles and tenant isolation are live. | In progress | Development | 0.16 | 2026-08-13 | 2026-08-13 | 1 | 20% | Back-office sign-in, roles and tenant isolation are live. Pending: PIN enforcement on the till, manager override for voids and discounts, an audit trail of who did what.
24 | Setup modules | Payment Mode Setup | Methods sync from the catalog and work on the till (cash, change, drawer, multi-tender). | In progress | Development | 0.16 | 2026-08-13 | 2026-08-13 | 1 | 55% | Methods sync from the catalog and work on the till (cash, change, drawer, multi-tender). Pending: a back-office editor to add, rename, reorder or retire one.
25 | Setup modules | Sales Type Setup | Types drive price tier, table service and the aggregator reference, all live. | In progress | Development | 0.16 | 2026-08-13 | 2026-08-13 | 1 | 50% | Types drive price tier, table service and the aggregator reference, all live. Pending: an editor — today a new delivery partner needs a database change.
26 | Setup modules | Modifiers Setup | The till asks them and products are assigned them in the product master. | In progress | Development | 0.16 | 2026-08-13 | 2026-08-13 | 1 | 60% | The till asks them and products are assigned them in the product master. Pending: authoring — creating a modifier group and its choices without touching the database.
27 | Setup modules | Report Category Setup | Categories exist, are assigned on products and filter the master. | In progress | Development | 0.33 | 2026-08-14 | 2026-08-14 | 1 | 40% | Categories exist, are assigned on products and filter the master. Pending: create, rename and merge; they are what every sales report groups by.
28 | Setup modules | Discount Setup | New. | Not started | Development | 0.33 | 2026-08-14 | 2026-08-14 | 1 | 0% | New. Discount master, line and bill level, percentage and amount, who may apply one, and how it is shown on a ZATCA invoice. Depends on Security for the override.
29 | Setup modules | Customer Setup | New. | Not started | Development | 0.33 | 2026-08-14 | 2026-08-14 | 1 | 0% | New. Customer master, phone lookup at the till, delivery addresses, and the VAT number a B2B customer needs on a standard tax invoice.
30 | Setup modules | Kiosk Setup | New. | Not started | Development | 2 | 2026-08-16 | 2026-08-17 | 2 | 0% | New. A fourth device role: self-order, self-pay, its own menu presentation and its own order-number stream.
31 | Devices | KDS Setup | The kitchen display runs, takes tickets, bumps and recalls. | In progress | Development | 1 | 2026-08-17 | 2026-08-17 | 1 | 45% | The kitchen display runs, takes tickets, bumps and recalls. Pending: back-office station configuration — today a station is created by the migration.
32 | Devices | CDS Setup | The customer display runs and follows the till. | In progress | Development | 1 | 2026-08-18 | 2026-08-18 | 1 | 40% | The customer display runs and follows the till. Pending: pairing and configuration in the back office, and what it shows between orders.
33 | Reporting | Reports | A dashboard and a sales list exist. | In progress | Development | 2 | 2026-08-19 | 2026-08-20 | 2 | 15% | A dashboard and a sales list exist. Pending: X and Z readings, sales by category, by hour and by cashier, VAT summary, and export.
34 | Compliance & release | ZATCA onboarding (phase 2) | Signing, the hash chain and the QR are built and tested. | Not started | Development | 1 | 2026-08-23 | 2026-08-23 | 1 | 0% | Signing, the hash chain and the QR are built and tested. Pending: real CSID onboarding through the Fatoora portal, encrypted key storage, and the sandbox run.
35 | Compliance & release | Arabic on receipts | Printer codepage and right-to-left shaping. | Not started | Development | 1 | 2026-08-24 | 2026-08-24 | 1 | 0% | Printer codepage and right-to-left shaping. A go-live blocker for a Saudi customer.
36 | Compliance & release | Android build | Tablets are the primary target and no APK can be produced yet: the Android SDK is not installed on the build machine.. | Not started | Development | 1 | 2026-08-25 | 2026-08-25 | 1 | 0% | Tablets are the primary target and no APK can be produced yet: the Android SDK is not installed on the build machine.
37 | Compliance & release | Single-instance guard | Two copies of the till open the same database. | Not started | Development | 1 | 2026-08-26 | 2026-08-26 | 1 | 0% | Two copies of the till open the same database. It has corrupted a device database once and produced two conflicting tills twice.
38 | Compliance & release | Zero-priced products review | 68 products carry no price on the paying tier and cannot be sold. | Not started | Development | 1 | 2026-08-27 | 2026-08-27 | 1 | 0% | 68 products carry no price on the paying tier and cannot be sold. Needs the customer to decide each one before go-live.
[5 empty] | TOTAL | 17.53 |  |  |  | 36.36% | Weighted by effort, so a large workstream counts for more than a small one.

## Summary
Summary
Every figure here is a formula over the Project Plan sheet.
By status
Status | Workstreams | Effort (days) | Share of effort
Done | 21 | 4.74 | 27.04%
In progress | 9 | 5.13 | 29.26%
Not started | 8 | 7.66 | 43.7%
TOTAL | 38 | 17.53 | 100%
By phase
Phase | Workstreams | Effort (days) | % complete
Foundations | 7 | 1.96 | 100%
Catalog & menu | 6 | 0.94 | 100%
Payments & service | 8 | 1.84 | 100%
Setup modules | 9 | 3.79 | 12.77%
Devices | 2 | 2 | 42.5%
Reporting | 1 | 2 | 15%
Compliance & release | 5 | 5 | 0%
Milestones
Milestone | Date | Basis
Project start | 2026-08-04 | First commit
Till selling on the real catalog | 2026-08-10 | 560 products, real prices, kitchen routing
Dine-in complete | 2026-08-11 | Floor, checks, merged tables, split bills
Setup modules complete | 2026-08-17 | End of the Setup modules phase — estimate
Reporting complete | 2026-08-20 | End of the Reporting phase — estimate
Ready for go-live | 2026-11-11 | After compliance and release work — ESTIMATE, and gated by ZATCA onboarding which needs the customer's Fatoora credentials

## Timeline
Timeline
One column per week. A bar is drawn by formula from the Start and Finish on the Project Plan sheet, so editing a date there redraws the bar here. |  | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-08-23 | 2026-08-30 | 2026-09-06 | 2026-09-13 | 2026-09-20 | 2026-09-27 | 2026-10-04 | 2026-10-11 | 2026-10-18 | 2026-10-25 | 2026-11-01
|  | 2026-08-08 | 2026-08-15 | 2026-08-22 | 2026-08-29 | 2026-09-05 | 2026-09-12 | 2026-09-19 | 2026-09-26 | 2026-10-03 | 2026-10-10 | 2026-10-17 | 2026-10-24 | 2026-10-31 | 2026-11-07
Workstream | Status | 02 Aug | 09 Aug | 16 Aug | 23 Aug | 30 Aug | 06 Sep | 13 Sep | 20 Sep | 27 Sep | 04 Oct | 11 Oct | 18 Oct | 25 Oct | 01 Nov
Architecture & repository | Done | bar: 2026-08-08
ZATCA signing on the device | Done | bar: 2026-08-08
Printer Setup | Done | bar: 2026-08-08
Windows desktop target | Done | bar: 2026-08-08
Till Setup / device enrolment | Done | bar: 2026-08-08
Back office foundation | Done | bar: 2026-08-08
Real catalog migration | Done | bar: 2026-08-08
Order numbers | Done | bar: 2026-08-15
Tablet schema migrations | Done | bar: 2026-08-15
Product master | Done | bar: 2026-08-15
Menu layout editor | Done | bar: 2026-08-15
Modifiers on the till | Done | bar: 2026-08-15
Button pictures | Done | bar: 2026-08-15
Payment Mode on the till | Done | bar: 2026-08-15
Dine-in: floor and checks | Done | bar: 2026-08-15
Tables pushed together | Done | bar: 2026-08-15
Floor areas | Done | bar: 2026-08-15
Split the check between guests | Done | bar: 2026-08-15
Table master | Done | bar: 2026-08-15
Branding on till and receipt | Done | bar: 2026-08-15
Receipt on screen | Done | bar: 2026-08-15
Employee Setup | In progress | bar: 2026-08-15
Security Setup | In progress | bar: 2026-08-15
Payment Mode Setup | In progress | bar: 2026-08-15
Sales Type Setup | In progress | bar: 2026-08-15
Modifiers Setup | In progress | bar: 2026-08-15
Report Category Setup | In progress | bar: 2026-08-15
Discount Setup | Not started | bar: 2026-08-15
Customer Setup | Not started | bar: 2026-08-15
Kiosk Setup | Not started | bar: 2026-08-22
KDS Setup | In progress | bar: 2026-08-22
CDS Setup | In progress | bar: 2026-08-22
Reports | In progress | bar: 2026-08-22
ZATCA onboarding (phase 2) | Not started | bar: 2026-08-29
Arabic on receipts | Not started | bar: 2026-08-29
Android build | Not started | bar: 2026-08-29
Single-instance guard | Not started | bar: 2026-08-29
Zero-priced products review | Not started | bar: 2026-08-29

## Assumptions
Assumptions, and how to read this plan
Where the delivered dates come from | The commit history of the repository, 4–12 August 2026. They are what happened, not estimates. Each delivered row names its commit in the Evidence column.
Where the remaining dates come from | Estimates, shown in blue everywhere they appear. They are the author's sizing of the remaining work, sequenced one item after another, and they are the least reliable numbers in this workbook.
Working week | Sunday to Thursday. Friday and Saturday are treated as the weekend. Public holidays are NOT deducted — add them and the finish dates move out.
Team size | One developer, working serially. Reports and Kiosk Setup share no dependencies with the setup modules, so a second developer could run them in parallel and pull the go-live date in by roughly three weeks.
What "In progress" means here | Part of the workstream is already live and part is not. The % complete column says how much, and the Notes column says exactly which part is missing. Six of the fourteen items on the client's list are in this state — none of them is starting from nothing.
What is NOT in the estimates | User acceptance testing, staff training, data cleansing beyond the 68 zero-priced products, hardware procurement, and on-site installation.
The dependency that is not ours | ZATCA phase-2 onboarding needs the customer's Fatoora portal credentials. Until those exist the till signs with a placeholder certificate, and no amount of development moves that date.
Additional items beyond the client's list | Arabic receipts, the Android build, the single-instance guard, ZATCA onboarding and the zero-priced product review are included because go-live depends on them. They were not on the list supplied.
Effort vs duration | Effort is working days of development. Calendar days on the plan sheet is the span from start to finish including weekends, and is a formula.